## 21June-27JuneTasksDetails
ID | Project | Subject | Type | Status | Author | Assignee | Accountable | Updated on | Created on
606341 | MERP Services | Challan Status PHP to Go | API Optimization | In Testing | Hrishabh Awadhiya | Pushkal Pandey | Rachita Mathur | 2026-06-24 12:17 | 2025-08-04 08:07
631204 | MERP Services | Proposal approval handling for cases where renewal is not generated | API Story | In Testing | Akash Devarapalli | Arjun Sharma | Garg Priya | 2026-06-26 07:54 | 2025-12-08 05:31
658150 | MERP Services | PHP to GO migration for - /index.php/proposal/listing/PaymentServices | API Optimization | Tested on LIVE | Sujal Chahande | Aman Kumar | Garg Priya | 2026-06-26 13:37 | 2026-04-21 04:36
658483 | MERP Services | PHP to GO Migration : /index.php/pay/ReceiptGeneration/ReceiptTagging | API Optimization | Tested on LIVE | Arjun Sharma | Arjun Sharma | Garg Priya | 2026-06-26 07:57 | 2026-04-22 04:55
659430 | MERP Services | php to golang /index.php/proposal/listing/ProposalConfirmationnew | Task | In Progress | Ramlal Suthar | Ramlal Suthar |  | 2026-06-22 05:59 | 2026-04-27 04:53
660145 | MERP Services | PHP to Golang migration : /index.php/userlist/CreateOpportunity | API Optimization | In Testing | Aman Kumar | Aman Kumar | Garg Priya | 2026-06-24 09:57 | 2026-04-29 04:58
661513 | MERP Services | PHP to GO Migration : /index.php/proposal/listing/Previewproposal | API Optimization | In Testing | Mohit Saini3 | Mohit Saini3 | Garg Priya | 2026-06-26 09:51 | 2026-05-06 05:07
663504 | MERP Services | PHP to GO Migration : /index.php/erp/OpportunityRemainderMailer/sendOpportunityEmails | API Optimization | In Testing | Arjun Sharma | Arjun Sharma | Garg Priya | 2026-06-26 07:55 | 2026-05-13 13:59
665343 | MERP Services | Tagged Invoice (Receipt) data is not showing, GLID: 43502687 | Task | To Do | Rakesh Ranjan | Tyagi Prajjwal |  | 2026-06-23 05:59 | 2026-05-19 09:45
665417 | MERP Services | MOD ID changes for Seller Info on android app and ios app | API Story | In Testing | Twinkle Jain | Ramlal Suthar | Vipul Bansal | 2026-06-23 10:46 | 2026-05-19 11:16
666502 | MERP Services | PHP to GO Migration : /index.php/nach/nachdeactivate | Task | In Progress | Shikha Pal | Shikha Pal |  | 2026-06-23 11:57 | 2026-05-25 03:53
667013 | MERP Services | PHP to GO Migration : /index.php/OVPValidation/validateOVPOnProposalCreation | API Optimization | In Testing | Arjun Sharma | Arjun Sharma | Garg Priya | 2026-06-26 07:54 | 2026-05-26 10:36
667379 | MERP Services | Ticket days logic Update for MERP | API Story | Peer / Code Review | Aditya Malik | Ramlal Suthar | Vipul Bansal | 2026-06-23 12:34 | 2026-05-27 10:06
667621 | MERP Services | Keys for hotlead removal after 14 day in companylisting API | API Story | In Development | Yash Srivastava | Vedant Kothawade | Rachita Mathur | 2026-06-25 11:37 | 2026-05-28 06:46
668017 | MERP Services | Request for IP Whitelisting – Company Search API (MERP Intermesh) | API Story | To Do | Duddu Yuvaraju | Kushagra Sharma | Hrishabh Awadhiya | 2026-06-23 06:40 | 2026-05-29 11:14
668113 | MERP Services | PHP to GO Migration : /index.php/pay/receiptGeneration/generatereceipt | Task | In Progress | Shikha Pal | Shikha Pal |  | 2026-06-23 07:13 | 2026-06-01 04:41
668308 | MERP Services | Addition of 'Paid Tenure' Subfilter in Priority Data Filter | API Story | In Development | Yash Chaturvedi | Vedant Kothawade |  | 2026-06-23 05:59 | 2026-06-01 08:59
668511 | MERP Services | API OPTIMIZATION [php to go] | API Optimization | In Testing | Prashant Kumar Saxena | Prashant Kumar Saxena | Hrishabh Awadhiya | 2026-06-23 08:08 | 2026-06-02 05:21
668683 | MERP Services | Indian BL DAU key in 12months/weeks Scorecard API | API Story | Product Confirmation | Sudhankar Singh | Arjun Sharma | Garg Priya | 2026-06-26 07:57 | 2026-06-02 10:15
668911 | MERP Services | Stopping internal emails to reduce email volume (CSD/KCD/Tele Annual verticals) | API Story | In Testing | Sonam Garg01 | Mohit Saini3 | Garg Priya | 2026-06-26 07:41 | 2026-06-03 05:45
669164 | MERP Services | Display Call Answer Metrics on Seller Contact Numbers on CSD MERP | API Story | In Development | Reetu Indiamart | Aman Kumar | Garg Priya | 2026-06-26 11:22 | 2026-06-03 12:11
669318 | MERP Services | Requirement: To modify Voicebot Lead Disposal API | API Story | BRD Reviewed By CF HOD | Harsh Pratap Mall |  | Rachita Mathur | 2026-06-24 11:44 | 2026-06-04 06:53
669350 | MERP Services | API OPTIMIZATION [php to go] | API Optimization | Ready for Production | Prashant Kumar Saxena | Prashant Kumar Saxena |  | 2026-06-25 11:10 | 2026-06-04 07:50
669493 | MERP Services | [Imp]: Internal Email Communication Optimization – Cost Reduction (CSD/KCD/Tele Annual verticals) | API Story | In Testing | Reetu Indiamart | Arjun Sharma | Vipul Bansal | 2026-06-26 05:08 | 2026-06-04 12:27
669603 | MERP Services | PHP to GoLang /index.php/erp/AWSWrapper/Activitychart API | Task | In Progress | Ramlal Suthar | Ramlal Suthar | Vipul Bansal | 2026-06-25 12:25 | 2026-06-05 06:30
669860 | MERP Services | PHP to Golang Migration : /index.php/proposal/Listing/AddProposalv1 | API Optimization | Product Confirmation | Aman Kumar | Aman Kumar | Garg Priya | 2026-06-24 10:35 | 2026-06-08 04:57
670324 | MERP Services | PHP to GO Migration : /index.php/pay/enach/Addnach | API Optimization | In Testing | Mohit Saini3 | Mohit Saini3 | Garg Priya | 2026-06-26 04:53 | 2026-06-09 06:31
670363 | MERP Services | Airtel double-leg C2C — customC2cCall API vendor branching + new post-call endpoint | API Story | SRS/API/Functional Document | devansh khandelwal | devansh khandelwal | Ramu Lath | 2026-06-22 13:48 | 2026-06-09 07:38
670371 | MERP Services | API Enhancement for MAP Price Exposure and Dynamic Rank Support in sellerMcatCityReport API | API Story | TC Creation | Ravideep singh | Aman Kumar | Garg Priya | 2026-06-23 08:39 | 2026-06-09 08:00
670372 | MERP Services | Movement of DWH API endpoint | Task | In Progress | Rachita Mathur | Vedant Kothawade | Rachita Mathur | 2026-06-22 04:58 | 2026-06-09 08:02
670781 | MERP Services | PHP to GO Migration : /index.php/salelist/automaturity | API Optimization | In Testing | Arjun Sharma | Arjun Sharma | Garg Priya | 2026-06-26 07:55 | 2026-06-10 10:39
670832 | MERP Services | Identify Correct Logic for Approved Score (TP) on DSR and TP Bifurcation | R & D | In Progress | Ansh Goyal | Prashant Kumar Saxena |  | 2026-06-23 06:55 | 2026-06-10 12:03
670903 | MERP Services | PHP to GO Migration : /index.php/pay/PackageDetail/showpackagedetail | Task | In Progress | Shikha Pal | Shikha Pal |  | 2026-06-24 10:04 | 2026-06-11 05:02
671001 | MERP Services | Proposal to Migrate 9696 PHP Wrappers to MERP API | API Story | Tested on LIVE | Rajeev Kumar | Prashant Kumar Saxena |  | 2026-06-26 04:25 | 2026-06-11 07:41
671273 | MERP Services | Display BLNI / Hidden BL marked by seller on CSD MERP | API Story | BRD Reviewed By CF HOD | Reetu Indiamart | Shikha Pal | Ramlal Suthar | 2026-06-23 03:49 | 2026-06-12 07:01
671415 | MERP Services | Making Deposit Bank Name dynamic - proforma/PostReceiptProposalNew | API Story | Ready for Production | Athulya Krishnan | Mohit Saini3 | Garg Priya | 2026-06-26 07:41 | 2026-06-12 11:32
671515 | MERP Services | Changes and Updates in "TAcustomers" API - Phase 2 | API Story | BRD Reviewed By Initiator HOD | Twinkle Jain | Venkatesh Vishwas | Tyagi Prajjwal | 2026-06-25 07:07 | 2026-06-15 03:47
671595 | MERP Services | Enable Full Ticket History Retrieval for LAST_TICKETS_CLM_FEEDBACK in KYC Details API | API Story | BRD Reviewed By Initiator HOD | Sindhuja Gaur | Prashant Kumar Saxena | Hrishabh Awadhiya | 2026-06-25 11:24 | 2026-06-15 06:40
671627 | MERP Services | Enabling 0–120 Upsell Filter & Case-Level Visibility in MERP | API Story | BRD Reviewed By CF HOD | Reetu Indiamart | Arjun Sharma | Garg Priya | 2026-06-26 08:04 | 2026-06-15 07:18
671658 | MERP Services | Inclusion of Catalog views in BL Consumed data on MERP | API Story | BRD Reviewed By Initiator HOD | Kritika Singh | Garg Priya | Vipul Bansal | 2026-06-26 08:14 | 2026-06-15 08:07
671861 | MERP Services | DWH APIs to Merp domain | Task | In Progress | Aman Kumar | Aman Kumar | Garg Priya | 2026-06-26 12:36 | 2026-06-16 04:59
672209 | MERP Services | DWH APIs to Merp domain | Task | In Progress | Mohit Saini3 | Mohit Saini3 | Garg Priya | 2026-06-26 04:57 | 2026-06-17 05:23
672273 | MERP Services | Updation of Prices for the provided services | API Story | Tested on LIVE | Neeraj Karakoti | Vedant Kothawade | Rachita Mathur | 2026-06-25 08:09 | 2026-06-17 06:48
672386 | MERP Services | Create Backend API for Dynamic/Ephemeral TURN Credentials for App Sharing Module | API Story | BRD Reviewed By CF HOD | Ravideep singh |  |  | 2026-06-26 07:22 | 2026-06-17 10:12
672514 | MERP Services | Stop Auto TBRO against Domain eKYC External Ticket closure | API Story | Tested on LIVE | Pavan Kumar | Prashant Kumar Saxena | Hrishabh Awadhiya | 2026-06-26 09:04 | 2026-06-17 12:40
672539 | MERP Services | API Requirement to Fetch Pricing from glcat_mcat_loc_price | API Story | In Development | Ansh Goyal | Aman Kumar | Garg Priya | 2026-06-26 07:37 | 2026-06-17 14:35
672679 | MERP Services | PHP to GO Migration :/index.php/fcp/PhnSearchNative | API Optimization | Product Confirmation | Shivam 03 | Shivam 03 |  | 2026-06-24 05:43 | 2026-06-18 09:38
673049 | MERP Services | Enable Instant Activation API for Winback | API Story | BRD Reviewed By CF HOD | Sakshi Sehajpal | Shivam 03 | Rachita Mathur | 2026-06-25 10:15 | 2026-06-19 12:19
673133 | MERP Services | Enhance gstuserdetails API Response with GST and CIN Information | Task | To Do | Shivam 03 | Shivam 03 |  | 2026-06-22 09:08 | 2026-06-22 05:37
673236 | MERP Services | Addition of TAN Verification Error Logs | API Optimization | To Do | Prateek Sharma | Rachita Mathur |  | 2026-06-22 07:58 | 2026-06-22 07:55
673712 | MERP Services | Enhancement in E-NACH Account Change API | Task | In Progress | Mrinal Kothari | Shikha Pal | Ramlal Suthar | 2026-06-26 05:20 | 2026-06-24 05:35
673716 | MERP Services | Show Last 7D¦30D¦90D BLNI in WebErp TopBar | API Story | BRD Reviewed By Initiator HOD | Sudhankar Singh | Shikha Pal | Ramlal Suthar | 2026-06-25 16:13 | 2026-06-24 05:39
673740 | MERP Services | Unified Location table & Location Standardization Framework | API Story | BRD Reviewed By Initiator HOD | Mehar Khurana |  |  | 2026-06-24 07:01 | 2026-06-24 06:19
673744 | MERP Services | Require Support for API's for IM AD pro service | Task | To Do | Sonam Garg01 | Arjun Sharma | Garg Priya | 2026-06-26 08:27 | 2026-06-24 06:25
673787 | MERP Services | Seller location display - top locations and glusr location on all -MERPs | API Story | BRD Reviewed By CF HOD | Reetu Indiamart | Aniket Mishra | Tyagi Prajjwal | 2026-06-25 11:05 | 2026-06-24 07:58
673794 | MERP Services | Latlong capture from CSD MERP during 'Company Search' and 'Global Search' | API Story | BRD Reviewed By CF HOD | Reetu Indiamart | Garg Priya | Vipul Bansal | 2026-06-26 11:11 | 2026-06-24 08:05
673822 | MERP Services | Need a api to rename iil_mod_fns_name column of iil_mod_fns table After Redash Datasource Rename | API Story | To Do | Abhishek Verma-DWH |  |  | 2026-06-24 08:52 | 2026-06-24 08:52
673948 | MERP Services | Renewalslist backend Details required | Task | To Do | Akshay Sethi |  |  | 2026-06-25 03:10 | 2026-06-25 03:10
673962 | MERP Services | Similar Paid Sellers Logic for Free Sellers | API Story | BRD Reviewed By CF HOD | Mehar Khurana |  |  | 2026-06-26 04:47 | 2026-06-25 04:44
674092 | MERP Services | Enhancement in /Userlisting/Employeedetails API to Return Structured Employee Attributes | API Story | To Do | Tirupati Raman Mishra |  |  | 2026-06-25 10:32 | 2026-06-25 09:43
674107 | MERP Services | Need GST information from PAN number | API Story | BRD Reviewed By CF HOD | Yash Srivastava |  |  | 2026-06-26 05:46 | 2026-06-25 10:32
674304 | MERP Services | Revision in TP for Photo Product Addition and Supplier Competition Activities | API Story | BRD Reviewed By Initiator HOD | Namit Maheshwari |  |  | 2026-06-26 11:59 | 2026-06-26 07:35
674315 | MERP Services | Usage of imdocs | Task | In Progress | Garg Priya | Arjun Sharma | Garg Priya | 2026-06-26 07:59 | 2026-06-26 07:59
674316 | MERP Services | Webhook id separation in eks repos | Task | To Do | Garg Priya | Arjun Sharma | Garg Priya | 2026-06-26 08:00 | 2026-06-26 08:00

## 21June-27JuneBugsDetails
ID | Project | Subject | Type | Status | Author | Assignee | Accountable | Updated on | Created on
642036 | MERP Services | CQS details API timeout errors | API Bug | In Progress | Nikul IM | Mohit Saini3 | Garg Priya | 2026-06-25 05:18 | 2026-02-02 11:41
667051 | MERP Services | Inconsistent behavior in PRESIGNED_URL key of preovp/preovpdata API | API Bug | In Progress | Aditya Malik | Shikha Pal | Vipul Bansal | 2026-06-25 11:46 | 2026-05-26 11:44
669855 | MERP Services | Discount API mismatch Between WEBERP and MERP proposal screen | API Bug | Replicate | Aditya Malik | Aman Kumar | Garg Priya | 2026-06-26 07:39 | 2026-06-08 04:48
669996 | MERP Services | Issue on Preview Proposal Screen for Industry Leader Value+ and Featured Leader Value+ Services. | API Bug | Tested & RCA Accepted | Aditya Malik | Mohit Saini3 | Garg Priya | 2026-06-26 07:48 | 2026-06-08 07:15
672454 | MERP Services | Address is inconsistent in fetchglusraddress API | API Bug | To Do | Aditya Malik | Aniket Mishra | Tyagi Prajjwal | 2026-06-25 11:07 | 2026-06-17 10:50
672485 | MERP Services | Unable to Approve Proposal for IL10 + Preferred Leader Pro Despite Active Base Service Requirement Validation | API Bug | Replicate | Aditya Malik | Arjun Sharma | Garg Priya | 2026-06-26 07:53 | 2026-06-17 11:46
673300 | MERP Services | Incorrect End Date in MDC PRO | API Bug | To Do | Yogesh Bhati | Tyagi Prajjwal | Vipul Bansal | 2026-06-25 05:13 | 2026-06-22 10:15
673727 | MERP Services | Live : Spacing Issue in Golang API Response and High Volume of 404 Errors Observed in New History API | API Bug | Tested & RCA Accepted | Dhanashri Hubali | Hrishabh Awadhiya | Hrishabh Awadhiya | 2026-06-26 05:30 | 2026-06-24 05:56
673842 | MERP Services | Incorrect Service Sale Issue for Nach Update Case | API Bug | Replicate | Kundan Jha | Mohit Saini3 | Garg Priya | 2026-06-26 08:27 | 2026-06-24 09:53
673969 | MERP Services | Re-Hosting Buttont Not visible | API Bug | Resolved on LIVE | maddineni nivas | Pushkal Pandey | Rachita Mathur | 2026-06-26 04:42 | 2026-06-25 05:01
673994 | MERP Services | NI, NP, and Wrong Number Dispositions Missing in Call Update Screen for >5 Cr Turnover Companies (Vertical 65) | API Bug | To Do | maddineni nivas | Vedant Kothawade | Rachita Mathur | 2026-06-25 05:56 | 2026-06-25 05:46
674066 | MERP Services | Appointment letter pdfs not generated from pdf_generation queue | API Bug | To Do | Nikita Kashyap | Aniket Mishra | Tyagi Prajjwal | 2026-06-25 08:11 | 2026-06-25 08:06
674101 | MERP Services | [Bi-Support] Call Tagging Issue | API Bug | To Do | Ajay Juyal | Hrishabh Awadhiya |  | 2026-06-25 10:16 | 2026-06-25 10:16